## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
USP Dependencies (By PI date)
To do:
USP Undertakers |  | for testing pick pred/succ with different dates, bring together start and end date columns, put go live date before |  | FA Legend: | Data Migration (DM) | Commercial Medical Product (CMP) | Data, Reporting and Analytics (RA) |  |  | Progress Legend: | On track |  |  | At risk |  |  | High Risk |  |  | Completed
Project lead: Chanita Sumar |  | Filtering on feature area |  |  | Quotes, Install and Bill (QIB) | Broker and Employer Experience (BEE) | Provider & Claim Payment+ (PCP)
Project Start Date: | 2022-05-31 | Organize ST by project connections - color grouping |  |  | Specialty (SP) | Member Experience (ME) | Scalability (SC) |  |  | PI Start: | May-31-22 | Aug-09-22 | Oct-18-22 | Jan-10-23 | Mar-21-23 | May-30-23 | Aug-08-23 | Oct-17-23 | Jan-09-24 | Mar-19-24 | May-28-24
[5 empty] | Consumer Engagement, Digital Therapeutic and Innovation Products (CE DTI) | Provider Experience (PE) | Benefit and Config (BC) |  |  | PI End: | Aug-08-22 | Oct-17-22 | Dec-26-22 | Mar-20-23 | May-29-23 | Aug-07-23 | Oct-16-23 | Dec-25-23 | Mar-18-24 | May-27-24 | Aug-05-24
Scrolling Increment: | 0 | Feature Area first column, ST ID and then Name comes after ID |  |  | Provider Optimization Cybertron (POC) | Ops Reporting (OR) |  |  |  |  | 2022-05-31 | 2022-08-09 | 2022-10-18 | 2023-01-10 | 2023-03-21 | 2023-05-30 | 2023-08-08 | 2023-10-17 | 2024-01-09 | 2024-03-19 | 2024-05-28
Feature Area | Strategic Theme ID | Name | Predecessors | Successors | Category | Progress | Start Date | End Date | Days | GoLive | PI40 | PI41 | PI42 | PI43 | PI44 | PI45 | PI46 | PI47 | PI48 | PI49 | PI50
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2022-07-04 |  |  |  |  | July | [27 empty] | August
Scrolling Increment: | 1 | time axis 2022-07-05 to 2022-08-29
Milestone description | Category | Assigned to | Progress | Start | Days | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
TITLE 1
Task 1 | Goal | Name | 40% | 2022-07-04 | 3 | T: 2; W: 2
Task 2 | Milestone |  |  | 2022-07-09 | 1 | bar: S
Task 3 | High Risk |  | 70% | 2022-07-01 | 10
Task 4 | Milestone |  |  | 2022-07-24 | 1 | bar: S
Task 5 | Med Risk |  | 10% | 2022-07-10 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2022-07-10 | 13
Task 2 | On Track |  | 50% | 2022-07-12 | 9
Task 3 | Low Risk |  | 33% | 2022-07-17 | 11
Task 4 | Milestone |  |  | 2022-07-19 | 1 | bar: T
Task 5 |  |  |  | 2022-07-20 | 24
TITLE 3
Task 1 | On Track |  |  | 2022-07-19 | 4
Task 2 | Med Risk |  |  | 2022-07-22 | 14
Task 3 | On Track |  |  | 2022-08-06 | 6
Task 4 | Goal |  |  | 2022-08-10 | 3 | W: 2; T: 2; F: 2
Task 5 | Low Risk |  |  | 2022-07-10 | 19
TITLE 4
Task 1 |  |  |  | 2022-08-13 | 15
Task 2 |  |  |  | 2022-08-27 | 5
Task 3 | Milestone |  |  | 2022-10-08 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Company name | [9 empty] | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2022-07-04 | [9 empty] | July | [27 empty] | August
Scrolling Increment: | 0 | time axis 2022-07-04 to 2022-08-28
Milestone description | Category | Assigned to | Progress | Column4 | Column5 | Column3 | Column2 | Column1 | Start | Days | time axis 2022-07-04 to 2022-08-28
TITLE 1
Task 1 | High Risk | Name | 25% | [5 empty] | 2022-07-04 | 3
Task 2 | Milestone | [7 empty] | 2022-07-09 | 1 | bar: 2022-07-09
Task 3 | Low Risk |  | 50% | [5 empty] | 2022-07-01 | 10
Task 4 | Milestone | [7 empty] | 2022-07-24 | 1 | bar: 2022-07-24
Task 5 | High Risk |  | 10% | [5 empty] | 2022-07-10 | 6
TITLE 2
Task 1 | High Risk |  | 60% | [5 empty] | 2022-07-10 | 13
Task 2 | On Track |  | 50% | [5 empty] | 2022-07-12 | 9
Task 3 | Low Risk |  | 33% | [5 empty] | 2022-07-17 | 11
Task 4 | Milestone | [7 empty] | 2022-07-19 | 1 | bar: 2022-07-19
Task 5 | [8 empty] | 2022-07-20 | 24
TITLE 3
Task 1 | On Track | [7 empty] | 2022-07-19 | 4
Task 2 | Med Risk | [7 empty] | 2022-07-22 | 14
Task 3 | On Track | [7 empty] | 2022-08-06 | 6
Task 4 | Goal | [7 empty] | 2022-08-10 | 3 | 2022-08-10: 2; 2022-08-11: 2; 2022-08-12: 2
Task 5 | Low Risk | [7 empty] | 2022-07-10 | 19
TITLE 4
Task 1 | [8 empty] | 2022-08-13 | 15
Task 2 | [8 empty] | 2022-08-27 | 5
Task 3 | Milestone | [7 empty] | 2022-10-08 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one